## Issues and decisions
№ | Issue | Opened | Owner | Due date | Status | Decision | Decided by | Decided on | Linked work and tickets
1 | What export format does accounting need? | 2026-11-04 | Analyst | 2026-11-11 | Decided | Excel in the accounting template, monthly | Finance director | 2026-11-10 | 2.1
2 | Who signs the acceptance certificate on the customer side? | 2026-11-05 | Project manager | 2026-11-16 | Open |  |  |  | 4.1
3 | Is a separate bench needed for load testing? | 2026-11-07 | QA engineer | 2026-11-14 | Open |  |  |  | 3.3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Instructions
Open issues and decisions log
Each issue is a row with an owner and a due date. When a decision is made, record it, who made it and when, and set the status to “Decided”.
Rows past their due date with the status “Open” turn red.
Link issues to plan work or tickets — that shows what is holding the date.
In Etapero open issues with owners, due dates, decisions and linked Jira tickets live in a project’s Issues section, and decisions on key issues show in the project overview. Loading the log from Excel into Etapero is not available yet.
An Etapero template — https://etapero.com/en/templates/. Free to use and change.