## Management plan
Section | The question the section answers | Answer or link to a document | Owner | Status
Goal and scope | What is the project’s goal and how will we know it is reached? |  |  | Not started
Goal and scope | What is in the project and what is not? |  |  | Not started
Goal and scope | Which deliverables go to the customer? |  |  | Not started
Work and schedule | Where are the work breakdown and the schedule kept? |  |  | Not started
Work and schedule | Which dates are approved as the baseline and who may change them? |  |  | Not started
Team | Who are the sponsor, the project manager and the workstream owners? |  |  | Not started
Team | Who makes which decisions (RACI)? |  |  | Not started
Risks | How are risks identified and rated, on which scales? |  |  | Not started
Risks | How often is the risk register reviewed and what happens to the red zone? |  |  | Not started
Communication | Which meetings do we hold, with whom and how often? |  |  | Not started
Communication | What is in the status report, who gets it and how often? |  |  | Not started
Communication | Where are documents, decisions and open issues kept? |  |  | Not started
Change | Who can propose a change and who approves it? |  |  | Not started
Change | How do we assess a change’s effect on date, budget and scope? |  |  | Not started
Control | How do we measure schedule variance and what counts as “at risk”? |  |  | Not started
Control | What are the acceptance criteria for deliverables? |  |  | Not started
Closure | How is the result accepted and what is handed over to operations? |  |  | Not started
Closure | When is the retrospective held and where are lessons kept? |  |  | Not started

## Instructions
Project management plan — checklist
The management plan answers not “what and when” but “how we run the project”. Go through the questions and write an answer or a link to a document.
Keep the plan short: the living parts — the schedule, risk register and open issues — are better kept in a system, with links from here.
More on each section: https://etapero.com/en/articles/project-management-plan/
In Etapero the work breakdown with its baseline, the risk register and open issues live in the system, and the project charter keeps the goal, sponsor and success criteria.
An Etapero template — https://etapero.com/en/templates/. Free to use and change.