## Plan
Code | Title | Type | Owner | Start | Finish | Work days | Predecessors | Status | Progress | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15
1 | Initiation | Phase |  | 2026-11-02 | 2026-11-09 |  |  | Not started | 0%
1.1 | Project charter | Task | Project manager | 2026-11-02 | 2026-11-05 | 3 |  | Not started | 0%
1.2 | Team and roles | Task | Project manager | 2026-11-06 | 2026-11-09 | 2 | 1.1 | Not started | 0%
1.3 | Project start | Milestone |  | 2026-11-09 | 2026-11-09 | 0 | 1.2 | Not started | 0%
2 | Planning | Phase |  | 2026-11-10 | 2026-11-25 |  |  | Not started | 0%
2.1 | Requirements | Task | Analyst | 2026-11-10 | 2026-11-19 | 8 | 1.3 | Not started | 0%
2.2 | Work breakdown and schedule | Task | Project manager | 2026-11-20 | 2026-11-25 | 4 | 2.1 | Not started | 0%
2.3 | Baseline approved | Milestone |  | 2026-11-25 | 2026-11-25 | 0 | 2.2 | Not started | 0%
3 | Execution | Phase |  | 2026-11-26 | 2027-01-15 |  |  | Not started | 0%
3.1 | Development | Task | Development team | 2026-11-26 | 2026-12-23 | 20 | 2.3 | Not started | 0%
3.2 | Documentation | Task | Technical writer | 2026-11-26 | 2026-12-07 | 8 | 2.3 | Not started | 0%
3.3 | Testing | Task | QA engineer | 2026-12-24 | 2027-01-15 | 10 | 3.1 | Not started | 0%
4 | Closure | Phase |  | 2027-01-18 | 2027-01-22 |  |  | Not started | 0%
4.1 | Acceptance | Task | Customer | 2027-01-18 | 2027-01-22 | 5 | 3.3;3.2 | Not started | 0%
4.2 | Project closed | Milestone |  | 2027-01-22 | 2027-01-22 | 0 | 4.1 | Not started | 0%

## Instructions
Project plan with a Gantt chart
The “Plan” sheet is a table in the Etapero import layout. Etapero recognises the Code, Title, Type, Owner, Start, Finish, Work days, Predecessors, Status and Progress columns itself.
The code sets the row’s place in the structure: 1 is a phase, 1.1 a piece of work inside it. Type: Phase, Work package, Task, Milestone or Goal. Dates are DD.MM.YYYY.
Predecessors are work codes separated by semicolons. Finish-to-start is assumed; other types are written the MS Project way: 1.2FF, 3SS.
The bars on the right are conditional formatting driven by the start and finish dates: change the dates and the bars move. Week headers are Mondays, the first in cell K1.
In Etapero: Structure → Import → “Upload an Excel or CSV file” → choose the “Plan” sheet → “By the row numbers of a column” → “Check what changes” → “Upload”. Etapero skips the week columns.
Excel does not recalculate dates from dependencies — Etapero does after the upload: moving one piece of work moves everything that depends on it, and the critical path is worked out itself.
An Etapero template — https://etapero.com/en/templates/. Free to use and change.