## Risk register
№ | Risk: cause → event → consequence | Category | Probability (1–5) | Impact (1–5) | Score | Zone | Owner | Response | Review date | Status | Linked work
1 | Because the contractor’s team is busy, integration may start late, which would move the pilot | Schedule | 4 | 4 | 16 | Red | Project manager | Agree a reserve with the contractor; weekly readiness check | 2026-11-16 | Open | 3.1
2 | Hardware delivery may slip and the test bench will not be ready in time | Supply | 3 | 4 | 12 | Amber | Procurement | Order three weeks early; find a second supplier | 2026-11-23 | Open | 3.3
3 | Requirements may change after the customer demo | Scope | 3 | 3 | 9 | Amber | Analyst | Early demos; a change control procedure | 2026-11-30 | Open | 2.1
4 | A key specialist may be on leave during acceptance | People | 2 | 3 | 6 | Green | Project manager | Check the leave schedule; name a deputy | 2026-12-07 | Open | 4.1
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Matrix
Number of risks by probability and impact
Probability ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 1 | 0
3 | 0 | 0 | 1 | 1 | 0
2 | 0 | 0 | 1 | 0 | 0
1 | 0 | 0 | 0 | 0 | 0

## Instructions
Risk register with a 5 × 5 matrix
Describe a risk as “cause → event → consequence”. Probability and impact are whole numbers from 1 to 5.
Score = probability × impact. Zones: 15 and above — red, 8–14 — amber, up to 7 — green. Change the thresholds in the Zone formulas and the conditional formatting.
The “Matrix” sheet counts the risks in each cell itself.
Review the register regularly and link risks to the work in the plan. More: https://etapero.com/en/articles/risk-register/
In Etapero the register of risks, problems and assumptions lives in a project’s Risks section, the matrix is built automatically, and red-zone risks show in the project overview and portfolio. Loading a register from Excel into Etapero is not available yet.
An Etapero template — https://etapero.com/en/templates/. Free to use and change.